## Overview
Iteration | Date | To-Do | Key Events
1 | 2017-05-15 | Proposal Preparation
Creation of Wiki Documentation
Learn Git, GitKraken, Slack, Trello
Learn Azure
Research on NodeJS and REACT
2 | 2017-05-29 | Proposal Finalization
Research on integrating ReactJS with Spring
Setting Up Git Repository
Setting Up Spring Architecture
Account Module I Registration,Login/Logout
3 | 2017-06-12 | Account Module II Forget Password, Remember Me, Amend Profile | Proposal Submission (19 June)
4 | 2017-06-26 | Project Module Create Project, Edit Project, Upload documents
Resource Module Create Resource, Edit Resource, Upload Documents
5 | 2017-07-10 | Search Module (Project)
6 | 2017-07-24 | Search Module (Resource)
Request Module (Project)
7 | 7th August | Request Module (Resource)
Dashboard
8 | 2017-08-21 | Project Management Module I | School Term Begins (21 August) Acceptance (22nd August)
9 | 4th September | Project Management Module II
10 | 18th September | Buffer
11 | 2nd October | Administration Module | Midterms (5-11 October)
Project Matching Module
12 | 2017-10-16 | Feedback & Ratings Module
13 | 2017-10-30 | Communications Module | Poster Day (30 October)
14 | 2017-11-13 | Bufer Iteration
15 | 2017-11-27 |  | Final (27 November - 4th December) Demo Event (4 December)